## Current Status
Sl No. | Activity | Activuty Driven By | Current Date | Current Status | Blockers | Steps taken to Resolve | Target Date
1 | Attended a meet and discussed the creation of first writing manual test cases, then the test cases that can be automated using Selenium and their implementation in Selenium IDE/Katalon Recorder, Eclipse. | Sayantan Bose,Supratim Bhui,Arnab Samanta,Sayantan Sarkhel,Debadri Mukherjee, Sarita Ghosh Shreya Chatterjee,Sourojit Nan | 27/11/2021 | Completed | None |  | 27/11/2021
2 | Prepared test case for 3 modules with Supratim Bhui | Sayantan Bose and Supratim Bhui | 28/11/2021 | Completed | None |  | 28/11/2021
3 | Prepared test case for 2 modules with Shreya Chatterjee | Arnab Samanta and Shreya Chatterjee | 29/11/2021 | Completed | invalid exceptions facing while working with java.awt.Robot class. |  | 15/11/2021
4 | Prepared test case for 3 modules with Debadri Mukherjee | Sarita Ghosh and Debadri Mukjerjee | 30/11/2021 | Completed | None |  | 30/11/2021
5 | Prepared test case for 2 modules with Sourojit Nan | Sourojit Nan and Sayantan Sarkhel | 31/11/2021 | Completed | None |  | 31/11/2021
6 | Prepared test case for 4 modules | Sayantan Bose | 2021-03-12 | Completed | Errors related to JavaScriptExecutor module. | Resolved the issue by adding proper dependencies. | 2021-03-12
7 | Prepared test case for 4 modules with Sarita Ghosh | Sarita Ghosh and Debadri Mukjerjee | 2021-04-12 | Completed | None |  | 2021-04-12
8 | Prepared test case for 3 modules with Sourojit Nan | Sourojit Nan and Sayantan Sarkhel | 2021-05-12 | Completed | None |  | 2021-05-12
9 | Creating manual testcases and preparing automation test scripts for 4 modules for DDT | Sayantan Bose | 2021-05-12 | Completed | Faced issues with DDT and Log4j.Some related issues while working with Apache POI. | Decided to do DDT in XML and resolved log4j issues in google meet | 14/12/2021
10 | Creating automation test scripts with Surojit Nan for 4 modules | Sayantan Sarkhel and Surojit Nan | 2021-06-12 | Completed |  | Decided to do DDT in XML and resolved log4j issues in google meet | 14/12/2021
11 | Creating manual testcases and preparing automation test scripts with Sarita Ghosh for 4 modules for DDT. | Debadri Mukjerjee and Sarita Ghosh | 2021-06-12 | Completed | Faced issues with DDT and Log4j.Some related issues while working with Apache POI. | Decided to do DDT in XML and resolved log4j issues in google meet | 14/12/2021
12 | Attended a meeting to resolve the problem of locally hosting the project | Sayantan Bose,Supratim Bhui,Arnab Samanta,Sayantan Sarkhel,Debadri Mukherjee, Sarita Ghosh Shreya Chatterjee,Sourojit Nan | 2021-07-12 | Completed | Faced problem while hosting the project on local server using XAMPP in PSL. | Decided to host the project on Local Host on our personal computer. | 2021-07-12
13 | Created the git repository | Debadri Mukjerjee | 2021-08-12 | In progress. | Some issues faced with git setup and push operation. | The parts done successfully pushed and commited. | 16/12/2021
14 | Attended a meet and discussed the creation of restapi testcases and their implementation in postman | Supratim Bhui, Arnab Samanta and Shreya Chatterjee | 2021-10-12 | Completed | None |  | 2021-10-12
15 | Working on POM structure and Extent Reports | Sayantan Bose and Sourojit Nan | 2021-11-12 | In progress. | Got some errors | Called a meet and discussed with team members,but still some work left. | 15/12/2021
16 | Working on Page Factory Model | Sarita Ghosh and Debadri Mukjerjee | 2021-12-12 | Completed | None |  | 2021-12-12
17 | Prepared API Testcase template | Supratim Bhui, Arnab Samanta and Shreya Chatterjee | 13/12/2021 | Completed | None |  | 13/12/2021
18 | Worked on API testing for 3 modules on Postman | Supratim Bhui | 14/12/2021 | Completed | was getting 401 unauthorized , and faced problems in getting the bearer token | went through the documentation and resolved the issue by issuing the token and the set that in the oAuth | 14/12/2021
19 | Worked on API testing for 3 modules on Postman | Shreya Chatterjee | 14/12/2021 | Completed | Faced issues with running test cases | The parts done sucessfully | 16/12/2021
20 | Worked on API testing for 3 modules on Postman | Arnab Samanta | 14/12/2021 | Completed | Faced issues with running test cases | Called a meet and resolved the issue | 14/12/2021

## Task Distribution
Selenium Automation Testing
Functionalitity | Date Assigned | Activity driven by | Current Status | Target Date
1. Login/ Sign- up events. | 2021-07-12 | Sayantan Bose | Completed | 2021-08-12
2. Browser Compatibility | 2021-07-12 | Sarita Ghosh | Conpleted | 2021-07-12
3. Home Page Functionality. | 2021-08-12 | Arnab Samanta and Supratim Bhui | Completed | 2021-10-12
4. Click Events | 2021-08-12 | Sayamtan Sarkhel | Completed | 2021-08-12
5. Design/User-Interface (Display) | 2021-08-12 | Sourajit Nan | Completed | 2021-09-12
6. Integration with Platforms and Services | 2021-09-12 | Shreya Chatterjee | Completed | 2021-09-12
7. Push Notifications | 2021-09-12 | Debadri Mukherjee | Completed | 2021-10-12
8. My Info Section a)Personal Details section b)Contact Details section c)Qualifications section | 2021-10-12 | Debadri Mukherjee, Sayantan Bose | Completed | 2021-12-12
9. Admin Section | 2021-10-12 | Supratim Bhui | Completed | 2021-12-12
10. PIM Section a)Employee List b)Add Employee c)Reports | 2021-10-12 | Shreya Chatterjee, Sayantan Sarkhel, Sarita Ghosh | Completed | 13/12/2021
11. Leave section a) Apply Leave b) My Leave c) Entitlements d) Reports e) Configure f) Leave List g) Assign Leave | 2021-10-12 | Sayantan Bose, Debadri Mukherjee, Sourajit Nan, Arnab Samanta | In progress. | 14/10/2021
12. Time section a)Timesheets b)Attendance c)Project Reports d)Project Info | 13/12/2021 | Sayantan Bose, Debadri Mukherjee, Sourajit Nan, Arnab Samanta | Completed | 15/12/2021
13. Recruitment section a)Candidates b)Vacancies | 13/12/2021 | Sarita Ghosh,Sayantan Sakhel,Supratim Bhui | Completed | 14/12/2021
14. Directory | 14/12/2021 | Sayantan Bose | Completed | 16/12/2021
15. Performance section a) Manage Reviews b) Employee Trackers | 14/12/2021 | Sayantan Bose,Shreya Chatterjee | completed | 16/12/2021
16. Buzz Section a)Update status post b)Upload/share video or image c)Like/Unlike, Expand action d)Share action e)Comment functionality | 13/12/2021 | Sarita Ghosh ,Debadri Mukherjee, Sourajit Nan, Arnab Samanta,Shreya Chatterjee | Completed | 16/12/2021
Rest Api Testing using Postman
Functionalitity | Date Assigned | Activity Driven By | Current Status | Target Date
SETUP | 2021-10-12 | Supratim Bhui, Arnab Samanta, Shreya Chatterjee | Completed | 2021-10-12
AUTH KEY | 2021-11-12 | Arnab Samanta | Completed | 2021-12-12
Global Variable | 2021-12-12 | Supratim Bhui, Arnab Samanta, Shreya Chatterjee | completed | 2021-12-12
Environment | 2021-12-12 | Arnab Chatterjee,Shreya Chatterjee | Completed | 2021-12-12
Admin Authorization | 13/12/2021 | Supratim Bhui,Sayantan Sarkhel, | completed | 14/12/2021
Employee | 13/12/2021 | Shreya Chatterjee, Sarita Ghosh | Completed | 15/12/2021
Leave | 13/12/2021 | Sayantan Bose, Debadri Mukherjee | Completed | 16/12/2021
Time | 13/12/2021 | Arnab Samanta , Sourajit Nan | Completed | 16/12/2021
Automated Test cases | 15/12/2021 | Arnab Samanta , Supratim Bhui, Shreya Chatterjee | Completed | 16/12/2021
Test result generated | 16/12/2021 | Arnab Samanta , Supratim Bhui, Shreya Chatterjee | Completed | 16/12/2021

## Concepts Used
S.No | Java | Status | Selenium | Status | Postman | Status
1 | Base Class | Done | wait | Done | Global Variable | Done
2 | Inheritence | Done | Implicit wait | Done | Query Parameters | Done
3 | Exception Handling | Done | Assert | Done | Basic Auth | Done
4 | Array<list> | Done | Actions class | Done | API Key Auth | Done
5 | Abstraction | Done | moveToElement | Done | Test Cases | Done
6 | Encapsulation | Done | Logger | Done | API Requests- get,post,put,Delete | Done
7 | String Concatenation | Done | TestNG | Done | Export Collection | Done
8 | Constructors | Done | Extent Report | Done | Import Collection | Done
9 | Method overloading | Done | Include/Exclude | Done | Authentication using bearer token | Done
10 | Method overriding | Done | Explicit Wait | Done | Automated Test cases | Done
|  |  | Window Handle | Done | JSON Schema Validation | Done
|  |  | Navigation across Browsers | Done | Team Workspaces | Done
|  |  | Css Selectors | Done | Environment variable | Done
|  |  | getCssValue | Done | we have test the curd operation and negetive test cases on every end point | Done
|  |  | Java Script Executer | Done | we have tested diff functionality on orangeHrm | Done
|  |  | Scroll down | Done
|  |  | from String | Done
|  |  | asHex | Done
|  |  | Xml Read/Write | Done
|  |  | WebDriver Manager | Done
|  |  | Screenshots | Done
|  |  | Dynamic Locators | Done
|  |  | xlsx Read/write using Apache POI (DDT) | Done
|  |  | Relative and Absolute x-paths | Done
|  |  | TestNG annotations, groups, Listemers. | Done
|  |  | Page Object Model | Done
|  |  | Page Factory Model | Done
|  |  | priorities_test | Done
|  |  | Parallel Tests, classes, methods | Done
|  |  | Run failed test cases | Done
|  |  | Maintaining logs using logs.xml | Done
|  |  | use of log4j.properties | Done
|  |  | Alerts | Done

## Rest
SL NO | Authorized Request | Test Case Details | Method Used | Modules
ADMIN AUTHORIZED
| 1.CRUD operations | get login page using url | GET | Admin Authorization
|  | Get Authentication key using client id,client secret and grant type | POST | Admin Authorization
|  | Get user details | GET | Admin Authorization
|  | Get organization details | GET | Admin Authorization
|  | Add employee using employee id | POST | Employee
|  | Get employee stutas using employee ID | GET | Employee
|  | Update employee details using employee id | PUT | Employee
|  | Terminate employeement using employee Iid | POST | Employee
|  | get dependency details using employee id | GET | Employee
|  | delete dependency using employee id | DELETE | Employee
|  | Serach employee using get method | GET | Employee
|  | Employee contact details using employee id | GET | Employee
|  | Save employee contact details | POST | Employee
|  | Update employee details using employee id | PUT | Employee
|  | get employee dependency using employee Id | GET | Employee
|  | update employee depenedency using employee id | PUT | Employee
|  | save employee dependency using employee id | POST | Employee
|  | get job details using employee id | GET | Employee
|  | save job details using POST methos | POST | Employee
|  | update job details using employee id | PUT | Employee
|  | Save leave Type using POST Method | POST | Leave
|  | type of leave Employee Get | GET | leave
|  | time period when employee gets leave | GET | Leave
|  | Create Entitlement using employee id | GET | Leave
|  | get customer using GET method | GET | Time
|  | create customer | POST | Time
|  | Update Customer details | PUT | Time
|  | delete customer | DELETE | Time
|  | Get activity using ID | GET | Time
|  | create activity using project id and name | POST | Time
|  | update activity using projectid and name | PUT | Time
|  | Delete Activity | DELETE | Time
|  | ccreate project using POST method | POST | Time
|  | Get project details | GET | Time
|  | update project details | PUT | Time
|  | delete project using projectid | DELETE | Time
| 2.Negatives Testcases | finding page using wrong hyperlink | GET | Admin Authorization
|  | Try to get Authentication key using wrong client id,client secret and grant type | POST | Admin Authorization
|  | User details with wrong information | GET | Admin Authorization
|  | Organization details with wrong information | GET | Admin Authorization
|  | add employee with negative value | POST | Employee
|  | get employee status with wrong employee id | GET | Employee
|  | update employee details with wrong id | PUT | Employee
|  | terminate employeement using Wrong details | POST | Employee
|  | get dependency with wrong details | GET | Employee
|  | delete dependent with wrong details | DELETE | Employee
|  | get employee contact details with wrong id | GET | Employee
|  | save employee details with wrong id | GET | Employee
|  | save employee details with wrong id | POST | Employee
|  | update details with wrong id | PUT | Employee
|  | get employee dependent with wrong details | GET | Employee
|  | update employee dependent with wrong information | PUT | Employee
|  | get job details with wrong id | GET | Employee
|  | Job details with wrong id | POST | Employee
|  | Create Entitlement using wrong details | POST | Leave
|  | Create leave type using wrong details | POST | Leave
|  | get leave type using wrong url | GET | Leave
|  | get leave period with wrong information | GET | Leave
|  | get customer details with wrong information | GET | Time
|  | create customer with same details | POST | Time
|  | Delete customer with wrong details | DELETE | Time
|  | Get activity with wrong value | GET | Time
|  | Get activity with wrong value | POST | Time
|  | update activity with negative testcase | PUT | Time
|  | Delete activity with negative test cases | DELETE | Time
|  | get project details with wrong url | GET | Time
|  | Create project with wrong admin id | POST | Time
|  | update details wring details | PUT | Time
|  | delete project with wrong id | DELETE | Time

## POM
Folder | Package/folder | Classes | Modules/File Content | Module/File Description
Mini_project_Grp_5 | Common | BaseClass.java | setup(String br)
tearDown()
captureScreen(WebDriver driver, String tname) throws IOException
String randomestring()
| Customizable_Emailable_Report | Add_Nationalities_Report.java | TC01_Report() throws Exception
WebElement findElement(By by) throws Exception
|  | Login_Test_Report.java | TC01_Report() throws Exception
WebElement findElement(By by) throws Exception
| data_driven_testing_DDT | Add_Nationality_Admin.java | Object[][] Authentication1() throws Exception
Test1(String TestURL,String UserName,String Password,String Nationality) throws Exception
WebElement findElement(By by) throws Exception
|  | Addphoto_Existing_Employee.java | hello()throws Exception
String getCellData(String xlFilePath, String sheetName,int rowNum,int column) throws Exception
WebElement findElement(By by) throws Exception
String getCellData(String xlFilePath, String sheetName,int rowNum,int column) throws Exception
WebElement findElement(By by) throws Exception
|  | Addphoto_New_Employee.java | WebElement findElement(By by)throws Exception
Object[][] Authentication1() throws Exception
AddEmployee_call_allmethods
openOrangeHRM()throws Exception
OrangeHRMlogin(String UserName,String Password)throws Exception
loseBrowser() throws Exception
PhotoUpload(String PhotoPath)throws Exception
addEmpdetails(String FirstName,String MiddleName,String LastName,String Id )throws Exception
Existing_Employee( )throws Exception
|  | File_Upload.java | WebElement findElement(By by)throws Exception
File_upload()throws Exception
PhotoUpload(String PhotoPath)throws Exception
|  | Login_function.java | hello()throws Exception
String getCellData(String xlFilePath, String sheetName,int rowNum,int column) throws Exception
WebElement findElement(By by) throws Exception
| Page_Factory_Model | Home_Page_1.java | Home_Page_1(WebDriver driver)
Logout() throws Exception
WebElement findElement(By by) throws Exception
|  | Login_Page_1.java | Login_Page_1(WebDriver driver)
Login() throws Exception
WebElement findElement(By by) throws Exception
|  | Nationalities_1.java | Nationalities_1(WebDriver driver)
AddNationality() throws Exception
WebElement findElement(By by) throws Exception
| Page_Objects | Admin_Page.java | Admin_Page (WebDriver driver)
Check_Job_Tab() throws Exception
WebElement findElement(By by) throws Exception
|  | Alternate_LoginPage.java | Alternate_LoginPage(WebDriver driver)
Login() throws Exception
WebElement findElement(By by) throws Exception
|  | Buzz_SectionPage.java | Buzz_SectionPage(WebDriver driver)
Check_Users() throws Exception
WebElement findElement(By by) throws Exception
|  | DirectoryPage.java | DirectoryPage(WebDriver driver)
AddDirectory() throws Exception
WebElement findElement(By by) throws Exception
|  | FileAttachmentPage.java | FileAttachmentPage(WebDriver driver)
Upload_File() throws Exception
Download_File() throws Exception
Delete_File() throws Exception
WebElement findElement(By by) throws Exception
|  | HomePage.java | HomePage(WebDriver driver)
Logout() throws Exception
WebElement findElement(By by) throws Exception
|  | LeavePage.java | LeavePage(WebDriver driver)
Leave() throws Exception
WebElement findElement(By by) throws Exception
|  | Login_Page.java | setUserName(String uname)
setPassword(String pwd)
clickSubmit()
WebElement findElement(By by) throws Exception
|  | MaintenancePage.java | MaintenancePage (WebDriver driver)
AddMaintenance() throws Exception
WebElement findElement(By by) throws Exception
|  | PerformancePage.java | PerformancePage(WebDriver driver)
AddEmployee_Review() throws Exception
WebElement findElement(By by) throws Exception
|  | PIM_SectionPage.java | PIM_SectionPage(WebDriver driver)
Check_Locations() throws Exception
WebElement findElement(By by) throws Exception
|  | Recruitment_Page.java | Recruitment_Page(WebDriver driver)
AddRecruitment() throws Exception
WebElement findElement(By by) throws Exception
|  | ReportsPage.java | ReportsPage(WebDriver driver)
Add_Employee_Reports() throws Exception
WebElement findElement(By by) throws Exception
|  | TimesheetsPage.java | TimesheetsPage(WebDriver driver)
Add_Timesheet() throws Exception
WebElement findElement(By by) throws Exception
|  | VacancyPage.java | VacancyPage(WebDriver driver)
AddVacancy() throws Exception
WebElement findElement(By by) throws Exception
| Screenshots_and_Extent_Reports | ExtentReport.java | ExtentReport()
String capture(WebDriver driver) throws IOException
String capture(WebDriver driver,String TestScriptName) throws IOException